## Slide 1
WP3 Monitoring and evaluation
in WP9
A.Vantarakis,
J. Velissari
DYPEDE/UPA

## Slide 2
Project monitoring, reporting and evaluation
WP3 monitoring and evaluation
in WP9
Deliverables
Activities
CA
Meetings
Guidelines
PFA development
Report on implemented actions
Recommendations on governance

## Slide 3
Project monitoring, reporting and evaluation
Table 3a : M&E aim in JAHEE project according the deliverables in each WP
WP | Deliverables & Milestones | Indicators | Tools | Timeframe | Minimal request | Target
9: Health and Equity in All Policies – Governance | PFA development | 1. Number (On/Off) | Report | Μ6 | 1 | 1
 | Report on implemented actions | 2. Number (On/Off) | Report | Μ33 | 1 | 1
 | Recommendations on governance | 3. Number (On/Off) | Report | M36 | 1 | 1

## Slide 4
Project monitoring, reporting and evaluation
M&E aim in JAHEE project according the activities
WP | Activities | Indicators | Tools | Timeframe | Minimal request | Target
9: Health and Equity in All Policies – Governance | CA | 1. CA (% completion) | Template/Checklist | M6 | 70% | 100%
 | Meetings | 2. % participation in the meetings | Reports/minutes | M36 | 70% | 80%
 | Guidelines | 3.% of institutions/public bodies approached saying they will adopt the guidelines | Questionnaire | M36 | 70% | 80%

## Slide 5
Prerequisites for each action
the activity feasible i.e. can it be done in the timespan of the JAHEE?
the activity derived from the analysis of the CA?
the activity is it in line with the objectives of the work package?
the activity directly or indirectly improve the health inequality monitoring system?
the activity is funded by non-European sources?
to have documented impact in health inequity and inequality in the specific WP
to add on a previous activity or to be a new one
to be evaluable